## Slide 1: Lecture No 14

## Slide 7
Activity | Time (days) (tij) | Earliest |  | Latest |  | Total Float (TF)
 |  | Start (ES) (Ei) | Finish (EF) Ei + tij | Start (LS) Lj - tij | Finish (LF) (Lj) | LS - ES
1-2 | 4 | 0 | 0 + 4 = 4 | 9 – 4 = 5 | 9 | 5 – 0 = 5
1-3 | 1 | 0 | 0 + 1 = 1 | 1 – 1 = 0 | 1 | 0 – 0 = 0
2-4 | 1 | 4 | 4 + 1 = 5 | 10 – 1 = 9 | 10 | 9 – 4 = 5
3-4 | 1 | 1 | 1 + 1 = 2 | 10 – 1 = 9 | 10 | 9 – 1 = 8
3-5 | 6 | 1 | 1 + 6 = 7 | 7 – 6 = 1 | 7 | 1 – 1 = 0
4-9 | 5 | 5 | 5 + 5 = 10 | 15 – 5 = 10 | 15 | 10 – 5 = 5
5-6 | 4 | 7 | 7 + 4 = 11 | 16 – 4 = 12 | 16 | 12 – 7 = 5
5-7 | 8 | 7 | 7 + 8 = 15 | 15 – 8 = 7 | 15 | 7 – 7 = 0
6-8 | 1 | 11 | 11 + 1 = 12 | 17 – 1 = 16 | 17 | 16 – 11 = 5
7-8 | 2 | 15 | 15 + 2 = 17 | 17 – 2 = 15 | 17 | 15 – 15 = 0
8-10 | 5 | 17 | 17 + 5 = 22 | 22 – 5 = 17 | 22 | 17 – 17 = 0
9-10 | 7 | 10 | 10 + 7 = 17 | 22 – 7 = 15 | 22 | 15 – 10 = 5

## Slide 8
Activity | Time (days) (tij) | Earliest |  | Latest |  | Total Float (TF)
 |  | Start (ES) (Ei) | Finish (EF) Ei + tij | Start (LS) Lj - tij | Finish (LF) (Lj) | LS - ES
1-2 | 4 | 0 | 0 + 4 = 4 | 9 – 4 = 5 | 9 | 5 – 0 = 5
1-3 | 1 | 0 | 0 + 1 = 1 | 1 – 1 = 0 | 1 | 0 – 0 = 0
2-4 | 1 | 4 | 4 + 1 = 5 | 10 – 1 = 9 | 10 | 9 – 4 = 5
3-4 | 1 | 1 | 1 + 1 = 2 | 10 – 1 = 9 | 10 | 9 – 1 = 8
3-5 | 6 | 1 | 1 + 6 = 7 | 7 – 6 = 1 | 7 | 1 – 1 = 0
4-9 | 5 | 5 | 5 + 5 = 10 | 15 – 5 = 10 | 15 | 10 – 5 = 5
5-6 | 4 | 7 | 7 + 4 = 11 | 16 – 4 = 12 | 16 | 12 – 7 = 5
5-7 | 8 | 7 | 7 + 8 = 15 | 15 – 8 = 7 | 15 | 7 – 7 = 0
6-8 | 1 | 11 | 11 + 1 = 12 | 17 – 1 = 16 | 17 | 16 – 11 = 5
7-8 | 2 | 15 | 15 + 2 = 17 | 17 – 2 = 15 | 17 | 15 – 15 = 0
8-10 | 5 | 17 | 17 + 5 = 22 | 22 – 5 = 17 | 22 | 17 – 17 = 0
9-10 | 7 | 10 | 10 + 7 = 17 | 22 – 7 = 15 | 22 | 15 – 10 = 5

## Slide 11
Q: Consider the following table summarizing the details of a project
Activity (here is 10 activities A to J) | Predecessor (s) | Duration (weeks) |  | 
 |  | O(optimistic time) | M (most likely time) | P (pessimistic time)
A | - | 5 | 6 | 7
B | - | 1 | 3 | 5
C | - | 1 | 4 | 7
D | A | 1 | 2 | 3
E | B | 1 | 2 | 9
F | C | 1 | 5 | 9
G | C | 2 | 2 | 8
H | E, F | 4 | 4 | 10
I | D | 2 | 5 | 8
J | H, G | 2 | 2 | 8
Construct the Project Network.
Find the expected duration and variance of each activity.
Find the Critical Path and expected project completion time.
What is the probability of completing the project on or before 22 weeks?

## Slide 13: Find the expected duration and variance of each activity
Activity (here is 10 activities A to J) | Predecessor (s) | Duration (weeks) |  |  | Expected duration OR Mean Duration (te ) | Variance
 |  | O(optimistic time) to | M (most likely time) tm | P (pessimistic time) tp | te = (to + 4tm + tp)/6 | 2 = [(tp –to)/6]2
A | - | 5 | 6 | 7 | (5+6*4+7)/6 = 6 | [(7-5)/6]2 = 0.11
B | - | 1 | 3 | 5 | (1+3*4+5)/6 = 3 | [(5-1)/6]2 = 0.44
C | - | 1 | 4 | 7 | (1+4*4+7)/6 = 4 | [(7-1)/6]2 = 1.00
D | A | 1 | 2 | 3 | (1+2*4+3)/6 = 2 | [(3-1)/6]2 = 0.11
E | B | 1 | 2 | 9 | (1+2*4+9)/6 = 3 | [(9-1)/6]2 = 1.78
F | C | 1 | 5 | 9 | (1+5*4+9)/6 = 5 | [(9-1)/6]2 = 1.78
G | C | 2 | 2 | 8 | (2+2*4+8)/6 = 3 | [(8-2)/6]2 = 1.00
H | E, F | 4 | 4 | 10 | (4+4*4+10)/6 = 5 | [(10-4)/6]2 = 1.00
I | D | 2 | 5 | 8 | (2+5*4+8)/6 = 5 | [(8-2)/6]2 = 1.00
J | H, G | 2 | 2 | 8 | (2+2*4+8)/6 = 3 | [(8-2)/6]2 = 1.00